## Sprint 1
| Epic | User Story | Status | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11
Carmen Accampo | Track Finch positions | As a finch researcher, I can view which bird was recorded on which camera | Active | 2023-09-21: Attend meeting, research Pinpoint and pyzbar (1h); 2023-09-22: Test Pyzbar vs OpenCV QR code detection reliability for images (1h); 2023-09-23: Test OpenCV image masking techniques to improve qr detection (1h); 2023-09-24: Display test results with matplotlib, OpenCV polylines, and other visualization tools (1.5h); 2023-09-26: Attend meeting; troubleshoot (1.5h); 2023-09-27: Add display options overlay for qr code frame and decoded string (2h); 2023-09-28: Client meeting (.5h); 2023-09-29: generate qr and data matrix codes and compare detection ability with visuals (3.5h); 2023-10-02: Bugfix and refactor (1h); 2023-10-04: Implement data matrix detection from live feed (1.5h); 2023-10-05: Meet with team (0.5hr); 2023-10-10: Meet with client, meet with team, code review (1.5hr)
Zach Burgess |  |  |  | 2023-09-21: Meeting (1h); 2023-09-23: Worked with Grant to setup the BigQuery and GCP connections, created rudementary QR codes using Python. Successfully loaded QR code data to BigQuery (5h); 2023-09-26: Meeting, works on GCP setup for myself and others (2h); 2023-09-28: Client meeting (.5h); 2023-09-29: Setup Jira Board (.5); 2023-10-03: Worked on setup of the Raspberry Pis (3hrs); 2023-10-06: Raspberry Pi research and initial setup hindered by lack of cables (1.5hrs); 2023-10-07: Setup Raspberry Pi, tested cables, attempted to boot OS (4hrs); 2023-10-08: Setup and successfully booted Raspberry Pi using wifi and established SSH connection (3hrs); 2023-10-09: Successfully established ethernet connection between laptops and Raspberry Pi (3hrs); 2023-10-10: Met with client, meet with team for code review, setup other member's with ethernet connections (2hrs)
David Schneidau |  |  |  | 2023-09-21: Meeting (1h); 2023-09-24: Tested yolov5 model for qr code detection (3.3h); 2023-09-26: Meeting, (1h); 2023-09-28: Client meeting (.5h); 2023-10-01: Setup traiangulator and distance algorithm for detection of actual cm between qr codes detected (7.5h); 2023-10-02: Finish 3d mappings for distance algorithm (1.5h); 2023-10-07: Setup Rpi cables testing, first OS boot attempt 6hr; 2023-10-10: Meet with client, meet with team, code review (1.5hr); 2023-10-11: Work on Rpi 2 hr
Grant Rainey |  |  |  | 2023-09-21: Attend meeting, research Pinpoint and pyzbar (1h); 2023-09-23: Set up BigQuery/GCP, Troubleshoot PyZbar/OpenCV, Sucessful proof-of-concept (6h); 2023-09-24: Set up positional data gathering, testing openCV for concurrent QR code detection(6h); 2023-09-26: Attend meeting; troubleshoot (1.5h); 2023-09-27: Set up GCP Service Account for IAM permsissions, encrypted keys for back-up/RPI credentials(1h); 2023-09-28: Client meeting (.5h); 2023-09-29: Began working on individualized bird summaries(1.5h); 2023-10-03: Work with Zach on RPI setup(2h); 2023-10-05: Meet with team (0.5hr); 2023-10-07: Set up RPI with team(2h); 2023-10-09: First POC version completed for individualized bird summaries(2.5h); 2023-10-10: Meet with client, meet with team, code review (1.5hr)