## Sprint 1
| Epic | User Story | Status | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21
Carmen Accampo | Track Finch positions | As a finch researcher, I can view which bird was recorded on which camera | Active | 2023-09-14: Research RPi OS through RPi Desktop (0.5h); 2023-09-15: Research OpenCV and test QR code detection (2h); 2023-09-17: Research RPi setup and components (1.5h); 2023-09-19: Review past research on finch tracking (1.5h); 2023-09-20: Research potential hardware issues and solutions; format submission (1h)
Zach Burgess | General Raspberry Pi Research | As a bird enjoyer, I can track birds more effectively if I understand how Raspberry Pis work | Active | 2023-09-15: Dug into basic implementations of Rasp Pis (1h); 2023-09-18: Researched QR extraction (1h); 2023-09-19: Read previous research paper on Finch Tracking (1h); 2023-09-20: Team Meeting (.5h), put together demo day stuff (1h); 2023-09-21: Team Meeting (.5h), polishing demo day stuff (1)
David Schneidau |  |  |  | 2023-09-14: Researched Basic Rpi info; 2023-09-18: QR code extraction and flattening and also remotely connecting to Rpi throgh python; 2023-09-19: Brainstormed possible options for making a dashbaord for displaying tabular results; 2023-09-20: Further research into outside possibiliities like RFID
Grant Rainey |  |  |  | 2023-09-14: Researched RPI integration/web server capabilities(1 hr); 2023-09-17: Researched computer vision frameworks, estimated compute/training requirements(1h); 2023-09-18: Researched Video/Image recognition cost/beneift(.5h); 2023-09-19: Researched RFID cost/benefit analysis(.5hr); 2023-09-20: Researched QR Code extraction/tracking libraries(pyzbar, zbar), explored PinPoint library and limitations(1.5h)