## Sprint 3
| Epic | User Story | Status | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02
Carmen Accampo |  |  |  |  | Attend meeting (0.5h) | Research ArUco (1h) |  |  | Test/Visualize ArUco detection compared with previously used (2h) | Progress check; organize detection tests file; add timer for different detection methods (2.5h) |  | Convert qr detection to aruco detection (detection) 1h | Convert qr detection to aruco detection (points calculation), troubleshoot (1.5h) | Convert qr detection to aruco detection (distances) (1.5h) | Simple point heatmap for aruco marker locations on live feed (1h) | Work on heatmap and distance traveled (1h) | Code review & meeting (1h) | Demo prep; research freezing python code (1h)
Zach Burgess |  |  |  | 2023-10-19: Attend meeting (0.5); 2023-10-21: researched methodology and alternatives behind running code on and offloading data from raspberry pis (2.5hrs); 2023-10-26: Worked with David to fix issues with code and worked with raspberry pis (5h); 2023-10-27: Researched and worked with raspberry Pis to run our code on the Pi (4h); 2023-10-28: began work on post processing of data once image capture process is complete (1h); 2023-10-30: Worked on running code on the Rpi w/ David and Grant (4hrs); 2023-10-31: Recorded code review + other meeting (1h); 2023-11-01: Successfully established BigQuery connection with Rpi and have the Rpi reading and uploading QR code information (5hrs); 2023-11-02: Demo Day Video and testing and prep (2 hr)
David Schneidau |  |  |  | 2023-10-19: Met with client and worked with Grant on testing and clarification (3.5h); 2023-10-23: Consolidated code and rewrote for memory/compute optimization. Reworked distances calculations to eliminate need to store frames. Rewrote camera functionality into a class format to make multi-camera deployment easy. (6.25hr); 2023-10-24: Worked with Grant to consolidate my new code into the google cloud BigQuery and testing and debugging (1.5hr); 2023-10-25: Debugging code and testing (2hr); 2023-10-30: Work on code and running on Rpi and testing (6 hr); 2023-10-31: Code review & meeting (0.5h); 2023-11-01: Troubleshoot distance algorithm (3.25 hr); 2023-11-02: Demo Day Video and testing and prep (2 hr)
Grant Rainey |  |  |  |  | Attend meeting, work with David to experiment with detection distances, reworking positional/distance calculation, reworking threading. (3.5h) |  | Experiment with reworking position calculation with overhead camera for computational optimization(1.5hr) | Researched memory optimization/offloading post processing(1h) | Worked with David to integrate BQ into position calculation code, creating new schema/database. rewrote and improved summary creation file based on new information, wrote center point calculation function for calculating distance between codes(3.5h) | Progress check; added timer for bigquery uploads(.5h) |  | Performed bug fixes on Birdsv3 with distance calculation, camera init, and BQ uploading. Spent 2 hours debugging GCP issues(3h) |  | Designed, built, and deployed docker file to container registry to resolve dependency issues on RPI architecture. Reworked main file for RPI and camera compatability(4h) |  | Worked on building a cross-architectural container to resolve dependency issues for RPI(3h) | Code review & meeting (0.5h) |  | Demo Day Video and testing and prep (2 hr)